## Sheet1
Team | Well name | Surface LSD | UWI | Target Formation | Rig Realease Date | Start | Finish | Duration | Comments | Frac Stages | Tonnage Per Stage | Tonnage | Planned Rate | Tracer | Laterel Length | License Number | Planned TD | Tie In | AFE Number | AFE Status
Frac Crew 1
SP | Steelman (08-30) Hz 09-29-004-03W2 | 00/08-30-004-03W2 | 101/09-29-004-03W2/00 | Marly | Thu 6/1/26 12:00 PM | 2026-06-05 14:00 | 2026-06-07 14:00 | 2 days |  | 25 | 5 | 125 | 1 | N/A | 4 | 408303 | 2901.12 | FL-100 | 20260113CM | FAPP
| Break |  |  |  |  | 2026-06-07 14:00 | 2026-06-13 14:00 | 6 days
FLP | Torquay (13-09) Hz 14-16-002-11W2 | 01/13-09-002-11W2 | 101/14-16-002-11W2/00 | Torquay | Sun 6/7/26 8:00 AM | 2026-06-13 14:00 | 2026-06-15 14:00 | 2 days |  | 50 KB* | 15 | 750 | 7 | N/A | 4 | 406883 | 3748.46 | FL-65 | 20260093CM | REL
| Break |  |  |  |  | 2026-06-15 14:00 | 2026-06-30 14:00 | 15 days
FLP | Torquay (16-09) Hz 01-04-002-11W2 | 02/16-09-002-11W2 | 101/01-04-002-11W2/00 | Torquay | Sat 6/20/26 8:00 AM | 2026-06-30 14:00 | 2026-07-04 14:00 | 4 days |  | 105 KB* | 15 | 1575 | 7 | N/A | 7 | 411460 | 5038.27 | FL-65 | 20260116CM | REL
Unscheduled
SP | Alameda (16-19) Hz 16-20-004-03W2 | 00/16-19-004-03W2 | 101/16-20-004-03W2/00 | Vuggy | Fri 5/22/26 12:00 PM | 2026-05-27 | 2026-05-29 | 2 days |  | 25 | 5 | 125 | 1 | N/A | 4 | 406662 | 2897.65 | FL-100 | 20260112CM | FAPP